## Sheet1
Product Name |  | Resume Craft | TC Start Date | 01.06.2024 | TC Execution Start Date | 01.06.2024 | TEST CASE SUMMARY
Module Name |  | Sing Up, Log In | TC End Date | 02.06.2024 | TC Execution End Date | 02.06.2024 | PASS | 11
Developer Name (TL) |  | x | Test Case Developed By | x | Browser (Tested) | Chrome | FAIL | 1
Test Executed By |  | Kazi Maharaf Islam | Test Case Reviewed By | x | Performance (Tested) | No | WARNING | 0
[7 empty] | TOTAL | 12
Test Case ID | Test Case Description | Test Data | Steps to Reproduce | Expected Result | Actual Result | Status | Remarks | Priority
TC-SU-001 | Verify sign up with invalid email address | vajovi7334acux@i.com | Go to Resumecraft.com Click on LogIn link Click on Sing Up button Fill up email with invalid email address Click on Sing Up button | User should get alert that Invalid email address | User dont get any alert | FAIL |  | LHLS
TC-SU-002 | Verify sign with valid email address | vajovi7334@acuxi.com | Go to Resumecraft.com Click on LogIn link Click on Sing Up button Fill up email with invalid email address Click on Sing Up button | User should get OTP through email | User gets OTP through email | PASS
TC-SU-003 | Verify OTP with invalid code | 22066 | Go to Resumecraft.com Click on LogIn link Click on Sing Up button Fill up email with invalid email address Click on Sing Up button Fillup with invalid OTP Click on "Active Account" button | User should get alert "invalid activation code" | User gets alert "invalid activation code" | PASS
TC-SU-004 | Verify OTP with valid code | 11066 | Go to Resumecraft.com Click on LogIn link Click on Sing Up button Fill up email with invalid email address Click on Sing Up button Fillup with invalid OTP Click on "Active Account" button | User should get alert "Your Account Successfully Active!" | User gets alert "Your Account Successfully Active!" | PASS
TC-SU-004 | After inserting Valid OTP login button works or not |  | Go to Resumecraft.com Click on LogIn link Click on Sing Up button Fill up email with invalid email address Click on Sing Up button Fillup with valid OTP Click on Login | Succefully logged in | Sucessfully logged in | PASS
TC-LI-001 | Verify login with Google button |  | Go to Resumecraft.com Click on LogIn link Click on Google button Select google account | Succefully logged in | Succefully logged in | PASS
TC-LI-002 | Verify login with invalid email address | vajovi7334@accuxi.com | Go to Resumecraft.com Click on LogIn link Fillup the email box with invalid email | User should get "invalid email or password" | User gets alert "invalid email or password" | PASS
TC-LI-003 | Verify login with valid email address | vajovi7334@acuxi.com | Go to Resumecraft.com Click on LogIn link Fillup the email box with valid email Fillup the password box with valid password | Succefully logged in | Succefully logged in | PASS
TC-LI-004 | Verify login with invalid password | kk1236 | Go to Resumecraft.com Click on LogIn link Fillup the email box with valid email Fillup the password box with invalid password | User should get "invalid email or password" | User gets alert "invalid email or password" | PASS
TC-LI-005 | Verify login with valid password | kk1234 | Go to Resumecraft.com Click on LogIn link Fillup the email box with valid email Fillup the password box with valid password | Succefully logged in | Succefully logged in | PASS
TC-LI-006 | Verify forget password |  | Go to Resumecraft.com Click on LogIn link Click on Forget Password Enter gmail account | User should get email with password reocovery link | User gets email with password reocovery link | PASS
TC-LI-007 | Verify recovery password link working |  | Go to email Open password recovery email Click on verify | User should be able to go to new tab with new password input | User able to go to new tab with new password input | PASS

## Sheet2
Test Case Report
Project Name | resumecreaft.com
Module Name | Sign Up and Log In
Test Case Version
Written By | Kazi Maharaf islam
Executed By | Kazi Maharaf islam
Reviewed By
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 11 | 1 | 0 | 0 | 16
Grand Total | 11 | 1 | 0 | 0 | 16
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.